ProxyMobile — 30-Day Launch Playbook

From zero to first paying customers: a day-by-day go-to-market plan

proxymobile.shop  •  Budget: $500–$2,000  •  July 2026

# 1. Campaign Overview

Campaign name: “Real SIMs. Real Sales.” — ProxyMobile 30-Day Launch

Summary: Turn proxymobile.shop from a finished product with zero sales into a business with paying customers, an affiliate engine, and a Telegram community — in 30 days, using channels where proxy buyers already are.

### Primary objective (SMART)

- 30–50 paying customers and $1,000–$2,000 in revenue within 30 days of launch, at a customer acquisition cost under $30.

### Secondary objectives

- 500+ members in the ProxyMobile Telegram channel

- 10+ active affiliates promoting your link

- 3–5 reseller/white-label partners signed (your reseller app is a moat — most competitors do not offer this)

- 20+ verified Trustpilot reviews as social-proof foundation

### Why this plan works

Proxy buyers do not discover services through Google ads (Google restricts proxy advertising, and search is dominated by incumbents). They discover them in Telegram groups, BlackHatWorld, Reddit, Discord cook groups, and via affiliate recommendations. Industry research shows most new proxy brands launch through BlackHatWorld marketplace threads rather than paid search. This plan concentrates your limited budget exactly there.

# 2. Target Audiences

Four segments, one product. Each has different pain points and hangouts — the same offer is framed differently for each.

| Segment | Pain point | Where they are | Hook |
| --- | --- | --- | --- |
| SMM / multi-account managers | Instagram/TikTok/FB bans from datacenter IPs | Telegram groups, SMM panels, BlackHatWorld | Real 4G/5G carrier IPs = trust score of a real phone |
| Scrapers / automation devs | Blocks, CAPTCHAs, paying for unused monthly plans | Reddit (r/webscraping), Discord, GitHub, HN | Pay-per-GB from $5 — no subscription, no waste |
| Sneaker / e-com botters | Datacenter IPs banned at checkout | Discord cook groups, Twitter/X | Mobile IPs pass where residential fails |
| Resellers / white-label | Want proxy income without infrastructure | BlackHatWorld, Telegram entrepreneur groups | Your own proxy shop, powered by our reseller platform |

Priority order for the first 30 days: (1) SMM managers — largest volume, fastest to convert via Telegram; (2) Resellers — highest lifetime value, and your reseller app is a unique differentiator; (3) Scrapers; (4) Botters.

# 3. Positioning & Key Messages

### Core message

“Real 4G/5G mobile proxies on real carrier SIMs, pay only for the gigabytes you use — from $5/GB, no subscription.”

### Supporting messages

- No subscription trap. Competitors bill $50–$100+/month whether you use it or not. ProxyMobile is pay-per-GB: top up, use, done.

- Real carrier IPs, not recycled pools. 4G/5G/LTE IPs that platforms treat like a real phone user. HTTP & SOCKS5, on-demand rotation.

- 9 countries, one wallet. Mobile + residential coverage across 9 countries from a single balance.

- Become a proxy seller yourself. White-label reseller platform: your brand, your prices, our network. (Lead message for the reseller segment.)

### Proof points to build ASAP

- Live speed/uptime test results posted weekly in Telegram

- Trustpilot reviews from first customers (ask every happy buyer, incentivize with bonus GB)

- Public 'IP quality' screenshots: fraud-score checks of your IPs vs. datacenter IPs

- A named human presence (you) answering in communities — trust sells proxies

# 4. Persuasion Engineering (the ethical kind)

You asked for social-engineering-level persuasion. The tactics below are the psychological levers that actually move proxy buyers — used honestly. The dishonest versions (fake reviews, astroturfing, spam) get you permanently banned from every community that matters and kill the brand. Don’t trade the business for week-one sales.

| Lever | How to apply it | Where |
| --- | --- | --- |
| Reciprocity | Free trial: 100–200 MB free on signup. Answer questions in communities generously before ever pitching. | Site, Telegram, Reddit |
| Social proof | Pin real reviews and payment screenshots (with permission) in Telegram; Trustpilot widget on site. | Telegram, site |
| Scarcity (real) | Launch offer capped: 'First 50 customers: 20% lifetime deposit bonus.' Count down publicly as slots fill. | Everywhere |
| Authority | Publish technical content: how mobile IP trust scores work, fraud-score comparisons. Be the expert, not the ad. | Blog, BHW, Reddit |
| Commitment | Small first yes: free trial → $10 top-up → regular usage. Never pitch the big package first. | Funnel |
| Community | Your Telegram channel is the product's home. Daily presence, fast support, insider tone. | Telegram |
| Risk reversal | 'First GB doesn’t perform? Money back, no questions.' Removes the #1 objection to unknown providers. | Site, sales chats |

# 5. Channel Strategy & Budget

Assumes a working budget of $1,500 (mid-range of $500–$2,000). Scale each line up or down proportionally.

| Channel | Budget | Play | Effort |
| --- | --- | --- | --- |
| BlackHatWorld | $150–250 | Marketplace sales thread (paid review required) + active posting in proxy sections. This is where new proxy brands launch. Run a launch giveaway in-thread. | High |
| Telegram (owned) | $0 | Your channel: daily posts, support bot, pinned offer, the OG-image ad you made. This is HQ. | High |
| Telegram shoutouts | $400 | Paid posts in 5–10 SMM/proxy/affiliate groups ($20–100 each). Test small, double down on what converts. | Medium |
| Affiliate program | $200 reserve | 30% first purchase + 10% recurring (market standard is 20–50% first). Recruit on BHW + Telegram. Affiliates are your unpaid sales force. | Medium |
| Influencer review | $300 | 1–2 sponsored honest reviews from a YouTube automation channel or established BHW/Telegram figure. | Medium |
| Reddit + Discord | $0 | Genuine participation in r/webscraping, r/proxies, automation Discords. Value first, signature/mention second. Never spam. | Medium |
| SEO / content | $0 | 2 posts/week targeting long-tail: 'best pay per GB mobile proxy', 'mobile proxy for Instagram 2026', '[country] mobile proxy'. Compounds after day 30. | Medium |
| Review platforms | $0 | Get listed: Trustpilot, Proxyway, affiliate.watch, comparison blogs (many accept submissions). | Low |
| Cold outreach | $0 | DM 10 SMM-panel owners and agency owners/day with a reseller pitch. Personalized, not templated blasts. | High |
| Trial data cost | $100 | Bandwidth given away in free trials and giveaways. | — |
| Contingency | $150–300 | Shift to whatever channel shows the best cost per customer in week 3. | — |

What’s deliberately missing: Google/Meta ads (proxy services are restricted categories and accounts get banned), mass DM spam (kills reputation), fake reviews (fraud, and communities detect it fast).

# 6. The 30-Day Calendar

Rhythm: Week 1 = foundation. Week 2 = seeding & community. Week 3 = launch push. Week 4 = affiliates, resellers, and doubling down on what works. Expect 1–3 hours/day.

## Week 1 — Foundation (Days 1–7)

| Day | Actions | Deliverable |
| --- | --- | --- |
| 1 | Conversion pass on the site: add free-trial offer, money-back line, Trustpilot placeholder, live chat/Telegram support button. Set up analytics (Plausible/GA4) + UTM links for every channel. | Site converts visitors; tracking live |
| 2 | Create the ProxyMobile Telegram channel + support account. Pin: what/why/launch offer. Post the ad image. Set up a simple support bot or your DM. | Telegram HQ live |
| 3 | Write launch offer: 'First 50 customers: 20% lifetime deposit bonus + free trial GB.' Draft BlackHatWorld sales thread (study top proxy threads' format first). | Offer + BHW thread draft |
| 4 | Register BHW account if needed, purchase marketplace thread review, submit. While waiting: complete profiles on Trustpilot, review sites, directories. | BHW thread submitted |
| 5 | Build affiliate program page (30% first / 10% recurring, payout terms, ready-made creatives incl. your ad image). Even a simple page + promo-code tracking works for v1. | Affiliate page live |
| 6 | Write blog post #1: 'Mobile vs. residential vs. datacenter proxies: what actually works for Instagram in 2026.' SEO-optimized, honest, cite data. | Post #1 published |
| 7 | Join 15–20 target communities (Telegram SMM groups, r/webscraping, r/proxies, 3–5 Discords, BHW sections). Just join, read, note rules and tone. Zero pitching. | Community map spreadsheet |

## Week 2 — Seeding & Community (Days 8–14)

| Day | Actions | Deliverable |
| --- | --- | --- |
| 8 | Start the daily habit (continues to day 30): answer 3–5 questions across communities helpfully, no links unless asked. Post daily in your own Telegram. | Daily presence begins |
| 9 | BHW thread goes live (typical review lag). Launch with a giveaway: '10 x 1GB free for commenters.' Reply to every comment within hours. | BHW launch + giveaway |
| 10 | Recruit first 5 testers from giveaway/communities: free GB in exchange for honest public feedback (BHW comment, Trustpilot, or Telegram review). | First testimonials incoming |
| 11 | Research 15 Telegram groups that sell shoutouts (SMM, affiliate, proxy niches). Ask prices, pick 3 for a $100 total test. Book them. | Shoutout test booked |
| 12 | Blog post #2: '[Top country] mobile proxies: pricing, carriers, and setup' (pick your strongest country). Post technical IP fraud-score comparison in Telegram + BHW thread. | Post #2 + proof content |
| 13 | Cold outreach begins (continues daily): 10 personalized DMs/day to SMM panel owners, agency owners, existing proxy resellers. Pitch = reseller platform demo, not proxies. | Outreach pipeline sheet |
| 14 | Week-1 metrics review: visitors, trials, conversions by UTM. First shoutouts drop — watch which group converts. Kill/scale decisions. | Metrics dashboard v1 |

## Week 3 — Launch Push (Days 15–21)

| Day | Actions | Deliverable |
| --- | --- | --- |
| 15 | Deploy remaining shoutout budget (~$300) into the 2–3 groups that converted. Negotiate repeat-post discounts. | Scaled shoutouts |
| 16 | Approach 3–5 YouTube automation/make-money channels and BHW/Telegram figures for a sponsored honest review ($100–300). Provide free access + fact sheet. | Influencer deal(s) signed |
| 17 | Publish comparison page: 'ProxyMobile vs. [2 incumbent competitors]' — honest table incl. where they're better. Post to communities where allowed. | Comparison page live |
| 18 | Push Trustpilot: every customer so far gets a polite ask + small GB bonus for any honest review. Target: 10+ reviews this week. | Review base growing |
| 19 | Blog post #3: 'How to resell proxies with zero infrastructure' — SEO play for the reseller segment, funnels to reseller page. | Post #3 published |
| 20 | First reseller onboarding call(s) from cold outreach pipeline. Offer founding-partner terms: better rev share for first 5 resellers, locked for life. | 1–2 resellers signed |
| 21 | Week-2/3 review. Calculate cost per customer per channel. Reallocate contingency budget to the winner. | Reallocation decision |

## Week 4 — Scale What Works (Days 22–30)

| Day | Actions | Deliverable |
| --- | --- | --- |
| 22 | Affiliate recruitment drive: post the program on BHW affiliate section + Telegram affiliate groups. Personally invite your 10 most engaged community contacts. | 10+ affiliates |
| 23 | Influencer review(s) go live. Amplify everywhere: pin in Telegram, quote on site, clip for posts. | Review amplified |
| 24 | Launch a 72-hour flash promo for fence-sitters: bonus GB on first deposit. Announce in Telegram + BHW + shoutout in best group. Real deadline — honor it. | Urgency campaign |
| 25 | Blog post #4: honest '30 days of ProxyMobile: numbers, lessons, roadmap' build-in-public post. These earn massive goodwill + Reddit/HN traction. | Post #4 published |
| 26 | Email/DM every free-trial user who didn’t convert: 1-question survey ('what stopped you?') + small incentive to try again. Fix the #1 answer. | Churn insights |
| 27 | Reseller push #2: case study or demo video of the reseller platform using week-3 partners. Send to entire outreach pipeline. | Reseller funnel v2 |
| 28 | Flash promo ends. Post results honestly. Convert momentum into channel subscriptions: 'daily deals + uptime reports only in Telegram.' | Post-promo capture |
| 29 | Full 30-day metrics workup: revenue, customers, CAC per channel, affiliate performance, reseller pipeline value, review count, community sizes. | Final scorecard |
| 30 | Write the Month-2 plan in 1 page: keep top-2 channels, cut the rest, set new targets (2x customers, affiliate revenue share of total, 5+ resellers). | Month-2 plan |

# 7. Content Assets Checklist

| Asset | Notes | Priority |
| --- | --- | --- |
| Free-trial + launch-offer site banner | Above the fold on homepage | Must |
| BHW sales thread (long-form) | Study top-performing proxy threads' structure first | Must |
| Telegram channel + pinned post + bot | Your HQ; the ad image you generated is the cover | Must |
| Affiliate page + 3 ready-made creatives | Reuse the Higgsfield ad in 3 sizes | Must |
| 4 blog posts (days 6, 12, 19, 25) | SEO + authority; honest and technical | Must |
| Competitor comparison page | Honest, including their strengths | Should |
| IP fraud-score proof screenshots | Recurring weekly content | Should |
| Reseller demo video (3–5 min) | Screen recording is fine | Should |
| Shoutout ad copy (3 variants to A/B) | Different hooks: price / trust score / reseller | Must |
| 30-day build-in-public recap | Doubles as Reddit/HN content | Nice |

# 8. Success Metrics

| KPI | 30-day target | Tracked via |
| --- | --- | --- |
| Paying customers | 30–50 | Your dashboard |
| Revenue | $1,000–2,000 | Payments |
| CAC (blended) | < $30 | Spend ÷ customers |
| Free trials started | 150+ | Analytics + UTM |
| Trial → paid conversion | 20%+ | Funnel tracking |
| Telegram members | 500+ | Channel stats |
| Trustpilot reviews | 20+ (4.5+ avg) | Trustpilot |
| Active affiliates | 10+ | Promo-code sales |
| Resellers signed | 3–5 | Pipeline sheet |

Review cadence: 10 minutes daily (sales, trials, channel replies) + 1 hour weekly (days 14, 21, 29) for kill/scale decisions. The single most important number: cost per paying customer per channel.

# 9. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| BHW thread underperforms | It's one of six channels; giveaway + fast replies dramatically improve thread velocity. Double down on Telegram if it lags. |
| Shoutouts don't convert | That's why week-2 tests $100 before week-3 spends $300. Never commit budget before data. |
| Community bans for promotion | Value-first rule: 10 helpful posts before any mention. Read each community's promo rules on day 7. |
| Trial abuse (free GB farming) | Cap trial per payment fingerprint/IP; require account; keep trial small (100–200MB). |
| Support overwhelm at spike | Telegram bot for FAQ + canned responses; reseller partners handle their own customers. |
| Chargebacks/fraud buyers | Crypto + card mix; small first top-ups reduce exposure; clear ToS. |

# 10. Start Today: Day-1 Checklist

- Add the free-trial offer and money-back guarantee to the homepage.

- Install analytics and create UTM links for: BHW, Telegram, Reddit, affiliates, shoutouts.

- Create the Telegram channel and post the launch ad you already have.

- Write the launch offer: first 50 customers, 20% lifetime deposit bonus.

- Open the BHW account and study the top 5 proxy sales threads.

Everything in this plan is reversible except lost time and lost reputation. Spend budget slowly, protect the brand's honesty fiercely, and let the data from days 14 and 21 tell you where month 2's money goes.